## GanttChart
Student Performance Analysis Project Schedule | [7 empty] | Gantt Chart Template © 2006-2025 by Vertex42.com.
SJSU CS-131
|  | Project Start Date | 2025-08-25 |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
|  | Project Lead | [5 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08 | [6 empty] | 2025-09-15 | [6 empty] | 2025-09-22 | [6 empty] | 2025-09-29 | [6 empty] | 2025-10-06 | [6 empty] | 2025-10-13
 | time axis 2025-08-25 to 2025-10-19
WBS |  | TASK | LEAD | START | END | DAYS | % DONE | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Sprint |  | Project Total |  | 2025-08-25 | 2025-12-20 | 5 | 6.667%
1 | 0 | Project Proposal |  | 2025-08-25 | 2025-09-08 | 14 | 33.33%
1.1 | 1 | Project Management (PM) | Lisa S. | 2025-08-25 | 2025-09-08 | 14 | 100%
1.1.1 | 2 | Adapt PM Template | Lisa S. | 2025-08-25 | 2025-09-08 | 14 | 100%
1.1.2 | 2 | Scope Week 1 Sprint | Lisa S. | 2025-08-25 | 2025-09-08 | 14 | 100%
1.1.3 | 2 | Define High Level Goals | Lisa S. | 2025-08-25 | 2025-09-08 | 14 | 100%
1.1.4 | 2 | Submit Sprint Tracking Board Link | Lisa S. | 2025-08-25 | 2025-09-08 | 14 | 100%
1.2 | 1 | Data Engineering (DE) | Alvin L. and Ola S. | 2025-08-25 | 2025-09-08 | 14 | 0%
1.2.1 | 2 | Find Accessible DataSet | Alvin L. and Ola S. | 2025-08-25 | 2025-09-08 | 14 | 0%
1.2.2 | 2 | Provide DataSet Link | Alvin L. and Ola S. | 2025-08-25 | 2025-09-08 | 14 | 0%
1.2.3 | 2 | Set Up GitHub Repository | Alvin L. and Ola S. | 2025-08-25 | 2025-09-08 | 14 | 0%
1.3 | 1 | Data Storytelling (DST) | Liru C. | 2025-08-25 | 2025-09-08 | 14 | 0%
1.3.1 | 2 | Project Proposal Writeup | Liru C. | 2025-08-25 | 2025-09-08 | 14 | 0%
2 | 0 | [Task Category] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.1 | 1 | [Task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.1.1 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.1.2 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.1.3 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.2 | 1 | [Task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.2.1 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.2.2 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.2.3 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.3 | 1 | [Task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.3.1 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.3.2 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
2.3.3 | 2 | [Sub-task] |  | 2025-09-08 | 2025-09-22 | 14 | 0%
3 | 0 | [Task Category] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.1 | 1 | [Task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.1.1 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.1.2 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.1.3 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.2 | 1 | [Task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.2.1 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.2.2 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.2.3 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.3 | 1 | [Task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.3.1 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.3.2 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
3.3.3 | 2 | [Sub-task] |  | 2025-09-22 | 2025-10-06 | 14 | 0%
4 | 0 | [Task Category] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.1 | 1 | [Task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.1.1 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.1.2 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.1.3 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.2 | 1 | [Task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.2.1 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.2.2 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.2.3 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.3 | 1 | [Task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.3.1 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.3.2 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
4.3.3 | 2 | [Sub-task] |  | 2025-10-06 | 2025-10-20 | 14 | 0%
5 | 0 | [Task Category] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.1 | 1 | [Task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.1.1 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.1.2 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.1.3 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.2 | 1 | [Task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.2.1 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.2.2 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.2.3 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.3 | 1 | [Task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.3.1 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.3.2 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
5.3.3 | 2 | [Sub-task] |  | 2025-10-20 | 2025-11-03 | 14 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: Task Lead Enter the name of the Task Lead in this column.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).

## TermsOfUse
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2025 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html